## Slide 1
ABC IT PMO: Management Report
Executive summary and items needing management attention
As of 2026-10-06
Prepared by PMO Agent
Source: board seed data, 8 tasks

## Slide 2
Executive summary
As of 2026-10-06
Chart: 
| Backlog | In Progress | Blocked | Done
Tasks | 3 | 2 | 2 | 1
8 tasks, 5 overdue
Executive Summary
• 25% blocked (2): escalate ABC-ITPM-0002 (Arjun Nair) to a sponsor; agree an unblock date.
• 37.5% backlog (3): start ABC-ITPM-0007 (Siti Rahman) now; pause ABC-ITPM-0004.
• 25% in progress (2): protect Michelle Goh's time on ABC-ITPM-0003; agree recovery date, add support.
Critical: needs management attention (4)
Rank | ID | Task | Owner | Due | Status | Score | Why | Redirect
1 | ABC-ITPM-0002 | CRITICAL Patch CVE-2025-41210 on branch teller VDI | Arjun Nair | 2026-09-10 | Blocked | 105 | Critical priority, overdue 26d, blocked, cybersecurity exposure | Escalate dependency to a sponsor; agree unblock date.
2 | ABC-ITPM-0007 | CRITICAL Complete MAS TRM compliance checklist | Siti Rahman | 2026-09-30 | Backlog | 81 | Critical priority, overdue 6d, compliance exposure | Start now; pause ABC-ITPM-0004 (lowest impact).
3 | ABC-ITPM-0005 | CRITICAL Vendor risk assessment — core switching provider | Priya Sharma | 2026-09-05 | Blocked | 65 | Medium priority, overdue 31d, blocked | Escalate dependency to a sponsor; agree unblock date.
4 | ABC-ITPM-0003 | CRITICAL UAT sign-off for mobile onboarding release 4.2 | Michelle Goh | 2026-09-25 | In Progress | 61 | High priority, overdue 11d | Protect owner's time; agree recovery date; add support.
As of 2026-10-06 | Data validated: 0 errors, 0 warnings | Source: board seed data (live board may differ)
Notes: Scoring rules: priority (Critical 40, High 25, Medium 10, Low 0) + 25 if overdue + 1 per day overdue (max 15) + 15 if Blocked + 10 for Compliance or Cybersecurity. Done tasks score 0. CRITICAL = not Done and (Critical priority or score >= 60); ranked by score, highest first.
Validation checks run: required fields; allowed values; IDs unique and format; dates real and not suspect; lengths; duplicates; reconciliation: status counts sum to total; reconciliation: overdue count recomputed independently; reconciliation: pie percentages sum to 100%; consistency: Done not overdue/critical. Result: Data validated: 0 errors, 0 warnings.
As-of date for overdue calculations: 2026-10-06. Source: seedTasks() in index.html, parsed by script.

## Slide 3
Thank you
Questions and discussion are welcome.
As of 2026-10-06